## Sheet1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Activity ID | Activity description | Duration |  |  | predecessors | Mitigation ID | Mitigation measure description | Mitigation duration |  |  | Cost |  |  |  | Relationships between measures and activities | Risk event ID | risk event description | risk event duration |  |  | Relationships between risk events and activities | Risk probability | Shared uncertainty ID | Shared uncertainty description | Durations of Shared uncertainties |  |  | Relations with activities
|  | Optimistic | Likely | Pessimistic |  |  |  | Minimum | Most likely | maximum | dependency factor (eta) | Minimum (not user input) | Most likely | Maximum (not user input) |  |  |  | Minimum | Most likely | maximum |  |  |  |  | Minimum | Most likely | maximum
1 | Contract date | 0 | 0 | 0 |  | 1 | Extra engineering design office personnel | 99.45 | 101.4 | 101.4 | 0.5 | 118846.1538 | 120000 | 120000 | 3 | 1 | Preliminary design rejection, including extra scope of works | 96 | 105 | 119 | 3 | 0.2
2 | Financial Close | 0 | 0 | 0 |  | 2 | Extra software design capacity | 13.65 | 13.65 | 13.65 | 0.5 | 30000 | 30000 | 30000 | 4 | 2 | EDP audit failure | 13 | 14 | 15 | 4 | 0.05
3 | Design | 819 | 920 | 1435 | 1 | 3 | Extra maintenance engineers | 103.35 | 126.75 | 126.75 | 0.5 | 136153.8462 | 150000 | 150000 | 7 | 3 | Existing condition Hollandse Brug deviates from maintenance plan made during tender phase | 63 | 70 | 78 | 7 | 0.15
4 | Obtaining Commencement Certificate | 105 | 130 | 194 | 1 | 4 | Extra administrators for permitting | 42.9 | 50.7 | 56.55 | 0.5 | 44307.6923 | 48000 | 50769.2308 | 8 | 4 | Unexpected gas conducts | 35 | 35 | 41 | 8 | 0.2
5 | Obtainment of Commencement Certificate | 0 | 0 | 0 | 4,2 | 5 | Applying extra preloading material | 40.95 | 50.7 | 50.7 | 0.5 | 677884.6154 | 750000 | 750000 | 9 | 5 | Lower consolidation rate than calculated for | 34 | 35 | 40 | 9 | 0.1
6 | Date of commencement | 0 | 0 | 0 | 5 | 6 | Adding extra on site construction flow | 91.65 | 101.4 | 107.25 | 0.5 | 190384.6154 | 200000 | 205769.2308 | 10 | 6 | Piling machines break down | 14 | 14 | 15 | 10 | 0.1
7 | Maintain existing road assets A9 / A1 / A6 | 976 | 1284 | 1836 | 6 | 7 | Extra prefab construcion capacity | 117 | 126.75 | 128.7 | 0.5 | 144230.7692 | 150000 | 151153.8462 | 11 | 7 | Late delivery of prefab elements | 19 | 21 | 25 | 11 | 0.2
8 | Conditioning, Cables and Conducts, permits | 168 | 200 | 268 | 6 | 8 | Extra M&E engineers | 50.7 | 50.7 | 50.7 | 0.5 | 60000 | 60000 | 60000 | 12 | 8 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 22 | 12 | 0.25
9 | Preload | 324 | 395 | 525 | 6 | 9 | Extra welding equipment and personnel | 52.65 | 64.35 | 64.35 | 0.5 | 90909.0909 | 100000 | 100000 | 14 | 9 | Production equipment failure | 20 | 21 | 23 | 14 | 0.05
10 | Construction of new Aqueduct | 200 | 260 | 341 | 6 | 10 | Extra temporary soil measures | 44.85 | 50.7 | 52.65 | 0.5 | 235576.9231 | 250000 | 254807.6923 | 15 | 10 | Construction site subsides | 13 | 14 | 15 | 15 | 0.05
11 | Construction of the Amsterdam-Rijn Canal bridge | 285 | 335 | 492 | 6 | 11 | Ancillary on standby | 200.85 | 202.8 | 222.3 | 0.5 | 199038.4615 | 200000 | 209615.3846 | 16 | 11 | Ancillary equipment failure | 33 | 35 | 41 | 16 | 0.1
12 | Road works southern A1 lane | 113 | 128 | 189 | 9,10,11 | 12 | Extra M&E engineers | 13.65 | 13.65 | 13.65 | 0.5 | 30000 | 30000 | 30000 | 18 | 12 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 21 | 18 | 0.25
13 | Commissioning of the southern A1 new lane | 0 | 0 | 0 | 12 | 13 | Extra excavation capacity | 95.55 | 101.4 | 101.4 | 0.5 | 121394.2308 | 125000 | 125000 | 20 | 13 | Discovery of polluted soil | 13 | 14 | 14 | 20 | 0.05
14 | Producing parts of Railbridge part 1 | 223 | 251 | 366 | 6 | 14 | Extra concrete workers / carpenters | 81.9 | 101.4 | 107.25 | 0.5 | 67788.4615 | 75000 | 77163.4615 | 21 | 14 | Concrete casting failure | 13 | 14 | 14 | 21 | 0.05
15 | Producing parts of Railbridge part 2 | 194 | 220 | 350 | 14 | 15 | Temporary ancillary construction and re-work | 70.2 | 76.05 | 83.85 | 0.5 | 1442307.6923 | 1500000 | 1576923.0769 | 22 | 15 | Main pillar subsides | 65 | 70 | 71 | 22 | 0.02
16 | Assembling a railway bridge on location | 559 | 674 | 971 | 14 | 16 | Extra excavation capacity | 60.45 | 76.05 | 81.9 | 0.5 | 134615.3846 | 150000 | 155769.2308 | 23 | 16 | Discovery of polluted soil | 25 | 28 | 32 | 23 | 0.05
17 | Moving Railway Bridge in place during Train Free Period | 0 | 0 | 0 | 16 | 17 | Extra asphalt equipment and personnel | 101.4 | 101.4 | 107.25 | 0.5 | 200000 | 200000 | 205769.2308 | 26 | 17 | Insufficient quality of base layer | 39 | 42 | 47 | 26 | 0.02
18 | Road works northern A1 lane | 109 | 130 | 191 | 17 | 18 | Extra removal works | 42.9 | 50.7 | 52.65 | 0.5 | 69230.7692 | 75000 | 76442.3077 | 28 | 18 | Discovery of asphalt with too high PAK percentage | 13 | 14 | 17 | 28 | 0.05
19 | Commissioning of the Northern A1 new lane | 0 | 0 | 0 | 18 | 19 | Extra equipment and personnel | 9.75 | 13.65 | 15.6 | 0.5 | 214285.7143 | 250000 | 267857.1429 | 30 | 19 | Additional scope of work (misc.) | 130 | 140 | 160 | 30 | 0.01
20 | Road and construction works new part junction Diemen | 477 | 530 | 848 | 13
21 | Build new viaducts A6 | 304 | 400 | 532 | 6
22 | Build second Hollandse bridge | 286 | 340 | 459 | 6
23 | Road and construction works junction Muiderberg | 716 | 930 | 1237 | 6
24 | Road works eastern part A6 | 90 | 100 | 130 | 21 22
25 | A6 East ready | 0 | 0 | 0 | 24
26 | Reconstruction western part A6 | 324 | 400 | 532 | 25
27 | Commissioning A6 | 0 | 0 | 0 | 18,23,26
28 | Road works existing part Diemen junction | 71 | 90 | 130 | 19,20
29 | Request Availability Certificate | 0 | 0 | 0 | 28
30 | Assess and obtain Availability Certificate | 16 | 20 | 27 | 29
31 | Demolition old A1 (part 1) | 54 | 61 | 91 | 30
32 | Demolition old A1 (part 2) | 23 | 30 | 48 | 31
33 | Greenery for old A1 | 77 | 90 | 129 | 31
34 | Applications and obtaining partial completion certificates | 104 | 120 | 161 | 30
35 | Request Completion Certificate | 0 | 0 | 0 | 33
36 | Assess and obtain Certificate of Completion | 17 | 20 | 27 | 35
37 | Scheduled Completion Date | 0 | 0 | 0 | 36
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =ROUND(RANDBETWEEN(130,160)/100*D7,0)
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =ROUND(RANDBETWEEN(130,160)/100*D6,0)