## Sheet1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Activity ID | Activity description | Duration |  |  | predecessors | Mitigation ID | Mitigation measure description | Mitigation duration |  |  | Cost |  |  |  | Relationships between measures and activities | Risk event ID | risk event description | risk event duration |  |  | Relationships between risk events and activities | Risk probability | Shared uncertainty ID | Shared uncertainty description | Durations of Shared activities |  |  | correlated activities
|  | Optimistic | Likely | Pessimistic |  |  |  | Minimum | Most likely | maximum | dependency factor (eta) | Minimum | Most likely | maximum |  |  |  | Minimum | Most likely | maximum |  |  |  |  | Minimum | Most likely | maximum
1 | Contract date | 0 | 0 | 0 |  | 1 | Extra engineering design office personnel | 51 | 52 | 52 | 0.5 | 118500 | 120000 | 120000 | 3 | 1 | Preliminary design rejection, including extra scope of works | 96 | 105 | 119 | 3 | 0.2
2 | Financial Close | 0 | 0 | 0 |  | 2 | Extra software design capacity | 7 | 7 | 7 | 0.5 | 30000 | 30000 | 30000 | 4 | 2 | EDP audit failure | 13 | 14 | 15 | 4 | 0.05
3 | Design | 865 | 920 | 1040 | 1 | 3 | Extra maintenance engineers | 53 | 65 | 65 | 0.5 | 148500 | 150000 | 156000 | 7 | 3 | Existing condition Hollandse Brug deviates from maintenance plan made during tender phase | 63 | 70 | 78 | 7 | 0.15
4 | Obtaining Commencement Certificate | 128 | 130 | 164 | 1 | 4 | Extra administrators for permitting | 22 | 26 | 29 | 0.5 | 44400 | 48000 | 49200 | 8 | 4 | Unexpected gas conducts | 35 | 35 | 41 | 8 | 0.2
5 | Obtainment of Commencement Certificate | 0 | 0 | 0 | 4,2 | 5 | Applying extra preloading material | 21 | 26 | 26 | 0.5 | 693750 | 750000 | 750000 | 9 | 5 | Lower consolidation rate than calculated for | 34 | 35 | 40 | 9 | 0.1
6 | Date of commencement | 0 | 0 | 0 | 5 | 6 | Adding extra on site construction flow | 47 | 52 | 55 | 0.5 | 195000 | 200000 | 200000 | 10 | 6 | Piling machines break down | 14 | 14 | 15 | 10 | 0.1
7 | Maintain existing road assets A9 / A1 / A6 | 1194 | 1284 | 1541 | 6 | 7 | Extra prefab construcion capacity | 60 | 65 | 66 | 0.5 | 139500 | 150000 | 157500 | 11 | 7 | Late delivery of prefab elements | 19 | 21 | 25 | 11 | 0.2
8 | Conditioning, Cables and Conducts, permits | 182 | 200 | 256 | 6 | 8 | Extra M&E engineers | 26 | 26 | 26 | 0.5 | 55500 | 60000 | 60000 | 12 | 8 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 22 | 12 | 0.25
9 | Preload | 363 | 395 | 486 | 6 | 9 | Extra welding equipment and personnel | 27 | 33 | 33 | 0.5 | 95816.7331 | 100000 | 103784.8606 | 14 | 9 | Production equipment failure | 20 | 21 | 23 | 14 | 0.05
10 | Construction of new Aqueduct | 234 | 260 | 325 | 6 | 10 | Extra temporary soil measures | 23 | 26 | 27 | 0.5 | 237500 | 250000 | 256250 | 15 | 10 | Construction site subsides | 13 | 14 | 15 | 15 | 0.05
11 | Construction of the Amsterdam-Rijn Canal bridge | 305 | 335 | 425 | 6 | 11 | Ancillary on standby | 103 | 104 | 114 | 0.5 | 185000 | 200000 | 206250 | 16 | 11 | Ancillary equipment failure | 33 | 35 | 41 | 16 | 0.1
12 | Road works southern A1 lane | 120 | 128 | 155 | 9,10,11 | 12 | Extra M&E engineers | 7 | 7 | 7 | 0.5 | 30000 | 30000 | 30000 | 18 | 12 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 21 | 18 | 0.25
13 | Commissioning of the southern A1 new lane | 0 | 0 | 0 | 12 | 13 | Extra excavation capacity | 49 | 52 | 52 | 0.5 | 112500 | 125000 | 128125 | 20 | 13 | Discovery of polluted soil | 13 | 14 | 14 | 20 | 0.05
14 | Producing parts of Railbridge part 1 | 241 | 251 | 279 | 6 | 14 | Extra concrete workers / carpenters | 42 | 52 | 55 | 0.5 | 75000 | 75000 | 76875 | 21 | 14 | Concrete casting failure | 13 | 14 | 14 | 21 | 0.05
15 | Producing parts of Railbridge part 2 | 209 | 220 | 279 | 14 | 15 | Temporary ancillary construction and re-work | 36 | 39 | 43 | 0.5 | 1450000 | 1500000 | 1500000 | 22 | 15 | Main pillar subsides | 65 | 70 | 71 | 22 | 0.02
16 | Assembling a railway bridge on location | 667 | 674 | 782 | 14 | 16 | Extra excavation capacity | 31 | 39 | 42 | 0.5 | 145000 | 150000 | 155000 | 23 | 16 | Discovery of polluted soil | 25 | 28 | 32 | 23 | 0.05
17 | Moving Railway Bridge in place during Train Free Period | 0 | 0 | 0 | 16 | 17 | Extra asphalt equipment and personnel | 52 | 52 | 55 | 0.5 | 182500 | 200000 | 200000 | 26 | 17 | Insufficient quality of base layer | 39 | 42 | 47 | 26 | 0.02
18 | Road works northern A1 lane | 120 | 130 | 147 | 17 | 18 | Extra removal works | 22 | 26 | 27 | 0.5 | 67500 | 75000 | 75000 | 28 | 18 | Discovery of asphalt with too high PAK percentage | 13 | 14 | 17 | 28 | 0.05
19 | Commissioning of the Northern A1 new lane | 0 | 0 | 0 | 18 | 19 | Extra equipment and personnel | 5 | 7 | 8 | 0.5 | 225000 | 250000 | 250000 | 30 | 19 | Additional scope of work (misc.) | 130 | 140 | 160 | 30 | 0.01
20 | Road and construction works new part junction Diemen | 519 | 530 | 620 | 13
21 | Build new viaducts A6 | 396 | 400 | 460 | 6
22 | Build second Hollandse bridge | 326 | 340 | 415 | 6
23 | Road and construction works junction Muiderberg | 856 | 930 | 1209 | 6
24 | Road works eastern part A6 | 100 | 100 | 116 | 21 22
25 | A6 East ready | 0 | 0 | 0 | 24
26 | Reconstruction western part A6 | 380 | 400 | 508 | 25
27 | Commissioning A6 | 0 | 0 | 0 | 18,23,26
28 | Road works existing part Diemen junction | 90 | 90 | 106 | 19,20
29 | Request Availability Certificate | 0 | 0 | 0 | 28
30 | Assess and obtain Availability Certificate | 19 | 20 | 23 | 29
31 | Demolition old A1 (part 1) | 57 | 61 | 71 | 30
32 | Demolition old A1 (part 2) | 29 | 30 | 35 | 31
33 | Greenery for old A1 | 82 | 90 | 107 | 31
34 | Applications and obtaining partial completion certificates | 119 | 120 | 149 | 30
35 | Request Completion Certificate | 0 | 0 | 0 | 33
36 | Assess and obtain Certificate of Completion | 18 | 20 | 24 | 35
37 | Scheduled Completion Date | 0 | 0 | 0 | 36
38 | End | 0 | 0 | 0 | 3 7 8 15 27 32 34 37
[11 empty] | 0 | 0 | 0