## Sheet1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Activity ID | Activity description | Duration (days) |  |  | Predecessor activities | Mitigation ID | Mitigation measure description | Mitigation capacity (days) |  |  | Mitigation cost (euros) |  |  |  | Relations with activities | Risk event ID | Risk event description | Risk duration (days) |  |  | Affected activities | Risk probability | Shared uncertainty factor ID | Shared uncertainty factor description | Shared uncertainty duration (days) |  |  | Relations with activities
|  | Optimistic | Most-Likely | Pessimistic |  |  |  | Minimum | Most likely | maximum | dependency factor (eta) | Minimum (not user input) | Most likely | Maximum (not user input) |  |  |  | Minimum | Most likely | maximum |  |  |  |  | Minimum | Most likely | maximum
1 | Contract date | 0 | 0 | 0 |  | 1 | Extra engineering design office personnel | 99.45 | 101.4 | 100 | 0.5 | 118846.1538 | 120000 | 119171.5976 | 3 | 1 | Preliminary design rejection, including extra scope of works | 96 | 105 | 119 | 3 | 0.2 | 1 |  | -45 | 0 | 72 | 10,11
2 | Financial Close | 0 | 0 | 0 |  | 2 | Extra software design capacity | 13.65 | 13.65 | 13.65 | 0.5 | 30000 | 30000 | 30000 | 4 | 2 | EDP audit failure | 13 | 14 | 15 | 4 | 0.05 | 2 |  | -50 | 0 | 100 | 21 22 23 7
3 | Design | 819 | 920 | 1435 | 1 | 3 | Extra maintenance engineers | 103.35 | 126.75 | 126.75 | 0.5 | 136153.8462 | 150000 | 150000 | 7 | 3 | Existing condition Hollandse Brug deviates from maintenance plan made during tender phase | 63 | 70 | 78 | 7 | 0.15 | 3 |  | -10 | 0 | 50 | 12 23
4 | Obtaining Commencement Certificate | 105 | 130 | 194 | 1 | 4 | Extra administrators for permitting | 42.9 | 50.7 | 56.55 | 0.5 | 44307.6923 | 48000 | 50769.2308 | 8 | 4 | Unexpected gas conducts | 35 | 35 | 41 | 8 | 0.2 | 4 |  | -45 | 0 | 110 | 20 26
5 | Obtainment of Commencement Certificate | 0 | 0 | 0 | 4,2 | 5 | Applying extra preloading material | 40.95 | 50.7 | 50.7 | 0.5 | 677884.6154 | 750000 | 750000 | 9 | 5 | Lower consolidation rate than calculated for | 34 | 35 | 40 | 9 | 0.1 | 5 |  | -20 | 0 | 100 | 15 16
6 | Date of commencement | 0 | 0 | 0 | 5 | 6 | Adding extra on site construction flow | 91.65 | 101.4 | 107.25 | 0.5 | 190384.6154 | 200000 | 205769.2308 | 10 | 6 | Piling machines break down | 14 | 14 | 15 | 10 | 0.1 | 6 |  | -5 | 0 | 100 | 16 20
7 | Maintain existing road assets A9 / A1 / A6 | 976 | 1284 | 1836 | 6 | 7 | Extra prefab construcion capacity | 117 | 126.75 | 128.7 | 0.5 | 144230.7692 | 150000 | 151153.8462 | 11 | 7 | Late delivery of prefab elements | 19 | 21 | 25 | 11 | 0.2 | 7 |  | -1 | 0 | 55 | 7 20
8 | Conditioning, Cables and Conducts, permits | 168 | 200 | 268 | 6 | 8 | Extra M&E engineers | 50.7 | 50.7 | 50.7 | 0.5 | 60000 | 60000 | 60000 | 12 | 8 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 22 | 12 | 0.25 | 8 |  | -20 | 0 | 50 | 8 9
9 | Preload | 324 | 395 | 525 | 6 | 9 | Extra welding equipment and personnel | 52.65 | 64.35 | 64.35 | 0.5 | 90909.0909 | 100000 | 100000 | 14 | 9 | Production equipment failure | 20 | 21 | 23 | 14 | 0.05 | 9 |  | -5 | 0 | 15 | 32 33
10 | Construction of new Aqueduct | 200 | 260 | 341 | 6 | 10 | Extra temporary soil measures | 44.85 | 50.7 | 52.65 | 0.5 | 235576.9231 | 250000 | 254807.6923 | 15 | 10 | Construction site subsides | 13 | 14 | 15 | 15 | 0.05 | 10 |  | 0 | 0 | 45 | 18 20
11 | Construction of the Amsterdam-Rijn Canal bridge | 285 | 335 | 492 | 6 | 11 | Ancillary on standby | 200.85 | 202.8 | 222.3 | 0.5 | 199038.4615 | 200000 | 209615.3846 | 16 | 11 | Ancillary equipment failure | 33 | 35 | 41 | 16 | 0.1 | 11 |  | -20 | 0 | 50 | 3 4
12 | Road works southern A1 lane | 113 | 128 | 189 | 9,10,11 | 12 | Extra M&E engineers | 13.65 | 13.65 | 13.65 | 0.5 | 30000 | 30000 | 30000 | 18 | 12 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 21 | 18 | 0.25 | 12 |  | -20 | 0 | 100 | 7 14
13 | Commissioning of the southern A1 new lane | 0 | 0 | 0 | 12 | 13 | Extra excavation capacity | 95.55 | 101.4 | 101.4 | 0.5 | 121394.2308 | 125000 | 125000 | 20 | 13 | Discovery of polluted soil | 13 | 14 | 14 | 20 | 0.05 | 13 |  | -80 | 0 | 90 | 7 16
14 | Producing parts of Railbridge part 1 | 223 | 251 | 366 | 6 | 14 | Extra concrete workers / carpenters | 81.9 | 101.4 | 107.25 | 0.5 | 67788.4615 | 75000 | 77163.4615 | 21 | 14 | Concrete casting failure | 13 | 14 | 14 | 21 | 0.05 | 14 |  | -140 | 0 | 100 | 7 23
15 | Producing parts of Railbridge part 2 | 194 | 220 | 350 | 14 | 15 | Temporary ancillary construction and re-work | 70.2 | 76.05 | 83.85 | 0.5 | 1442307.6923 | 1500000 | 1576923.0769 | 22 | 15 | Main pillar subsides | 65 | 70 | 71 | 22 | 0.02
16 | Assembling a railway bridge on location | 559 | 674 | 971 | 14 | 16 | Extra excavation capacity | 60.45 | 76.05 | 81.9 | 0.5 | 134615.3846 | 150000 | 155769.2308 | 23 | 16 | Discovery of polluted soil | 25 | 28 | 32 | 23 | 0.05
17 | Moving Railway Bridge in place during Train Free Period | 0 | 0 | 0 | 16 | 17 | Extra asphalt equipment and personnel | 101.4 | 101.4 | 107.25 | 0.5 | 200000 | 200000 | 205769.2308 | 26 | 17 | Insufficient quality of base layer | 39 | 42 | 47 | 26 | 0.02
18 | Road works northern A1 lane | 109 | 130 | 191 | 17 | 18 | Extra removal works | 42.9 | 50.7 | 52.65 | 0.5 | 69230.7692 | 75000 | 76442.3077 | 28 | 18 | Discovery of asphalt with too high PAK percentage | 13 | 14 | 17 | 28 | 0.05
19 | Commissioning of the Northern A1 new lane | 0 | 0 | 0 | 18 | 19 | Extra equipment and personnel | 9.75 | 13.65 | 15.6 | 0.5 | 214285.7143 | 250000 | 267857.1429 | 30 | 19 | Additional scope of work (misc.) | 130 | 140 | 160 | 30 | 0.01
20 | Road and construction works new part junction Diemen | 477 | 530 | 848 | 13
21 | Build new viaducts A6 | 304 | 400 | 532 | 6
22 | Build second Hollandse bridge | 286 | 340 | 459 | 6
23 | Road and construction works junction Muiderberg | 716 | 930 | 1237 | 6
24 | Road works eastern part A6 | 90 | 100 | 130 | 21 22
25 | A6 East ready | 0 | 0 | 0 | 24
26 | Reconstruction western part A6 | 324 | 400 | 532 | 25
27 | Commissioning A6 | 0 | 0 | 0 | 18,23,26
28 | Road works existing part Diemen junction | 71 | 90 | 130 | 19,20
29 | Request Availability Certificate | 0 | 0 | 0 | 28
30 | Assess and obtain Availability Certificate | 16 | 20 | 27 | 29
31 | Demolition old A1 (part 1) | 54 | 61 | 91 | 30
32 | Demolition old A1 (part 2) | 23 | 30 | 48 | 31
33 | Greenery for old A1 | 77 | 90 | 129 | 31
34 | Applications and obtaining partial completion certificates | 104 | 120 | 161 | 30
35 | Request Completion Certificate | 0 | 0 | 0 | 33
36 | Assess and obtain Certificate of Completion | 17 | 20 | 27 | 35
37 | Scheduled Completion Date | 0 | 0 | 0 | 36
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID's of the activities. Keep the ID's in order starting from 1
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description of project activities. It is not an essential input.
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Activities durations: three estimates Note that the three estimates must be in ascending order: minimum <= Most-likely <= maximum
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The ID's of the predecessor activities of each activity. This helps to define dependencies and to generate the project network diagram . This is a user input. You may insert more than one predecessor by separating them with a space or a comma
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID's of the mitigation measures. Keep the ID's in order starting from 1
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description of mitigation measures activities. It is not an essential input.
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mitigation capacity of the mitigation measures: three estimates. The mitigation capacity is the duration reduced from the total duration of the influenced activity Note that the three estimates must be in ascending order: minimum <= Most-likely <= maximum
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost of excecuting a mitigation measure
Note on P2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The ID's of activities that are influenced by each mitigation measure. One Mitigation measure can influence (i.e., reduce the time of) one or more activities. You may insert more than one activity by separating them with a space or a comma.
Note on Q2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID's of the risk events. Keep the ID's in order starting from 1
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description of risk events. It is not an essential input.
Note on S2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The delay induced by each risk event: three estimates. Note that the three estimates must be in ascending order: minimum <= Most-likely <= maximum
Note on V2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The ID's of activities that are impacted by each risk event. One risk event can impact (i.e., increase the time of) one or more activities. You may insert more than one activity by separating them with a space or a comma.
Note on W2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the probability that a risk event will occur. This is a user input between 0 and 1.
Note on X2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID's of the shared uncertainty factors. Keep the ID's in order starting from 1
Note on Y2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description of the shared uncertainity factors. It is not an essential input. Uncertainty factors can have an impact on the duration of construction activities. These factors may simultaneously influence multiple activities Note that the correlation section is only necessary for the advanced version of the MitC (not the basic)
Note on Z2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Duration of the uncertainty factors: three estimates. Note that the three estimates must be in ascending order: minimum <= Most-likely <= maximum
Note on AC2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The ID's of correlated activities that share the uncertainty factor. This is a user input. You may insert more than one activity by separating them with a space or a comma.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D7,0)
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely duration of the activity. The user must define this quantity
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D6,0)
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (pessimistic) capacity of the mitigation measure. The user must define this quantity.
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely capacity of the mitigation measure. The user must define this quantity.
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (optimistic) capacity of the mitigation measure. The user must define this quantity.
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This factor defines to what extent the mitigation cost variation depends on the mitigation capacity variation. This factor is between 0 and 1. If this factor is set to 1, then the mitigation cost increases/decreases proportionally to the increase/decrease in he mitigation capacity. If it is set to 0, then the cost will remain constant regardless of the variation in the mitigation capacity. You may set any number between 0 and 1 (i.e., 0.5 means partial relation between the cost variation and the mitigation variation)
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minimum cost of the mitigation measure. This is not a user input. It is automatically computed following a predefined formula. To add more cost items to the list, you may copy the formula from any of the cells below.
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Most-likely cost of the mitigation measure. This is a user input.
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maximum cost of the mitigation measure. This is not a user input. It is automatically computed following a predefined formula. To add more cost items to the list, you may copy the formula from any of the cells below.
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (optimistic) delay induced by the risk event. The user must define this quantity.
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely delay induced by the risk event. The user must define this quantity.
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (pessimistic) delay induced by the risk event. The user must define this quantity.
Note on Z3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minimum duration of the uncertainty factor. This is a user input.
Note on AA3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Most-likely duration of the uncertainty factor. This number is to set to 0. We only care about the variation in duration.
Note on AB3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maximum duration of the uncertainty factor. This is a user input.